## Sheet1
Date | Time Spent | Time payable | Status Description
2020-09-21 | 90 | 90 | Finished Navbar and feutures in the homepage.
2020-09-22 | 180 | 90 | Finished Footer in the homepage. Added Navber and feutures in the menu page, and started on the menu card. Refactoring
2020-09-23 | 180 | 180 | Continued on the menu card. Refactoring
2020-09-24 | 180 | 90 | Finished menu card and refactoring. Implemented Search functionality in the menu page, but there is still a bug. Register and Login page done.
2020-09-25